## Revision History
Work Product: | QA Estimate
Project : | QA Ecommerce Project
WBS Code : | QAP1536
Customer : | BlazeCo.
Revision : | V1
Author/Updater: | James Ugdang
Revision | Date (the date you worked on it) | Comments (Explain the changes you made)
0.1 | 2024-11-08 | Fleshed out Description on the 'Detailed Estimate' sheet and added the test cases and included the estimated time (in minutes) for Build 1 in the 'Write' and 'Estimate' columns.
1 | 2024-11-09 | Finished adding the test cases and included the estimated time (in minutes) for Build 1 in the 'Write' and 'Estimate' columns.
1.1
1.2
1.3
1.4
1.5
Revision History

## Detailed Estimate
Description | Release Phase | Priority | Write (min) | Execute (min) | Total (min)
QA Ecommerce Project | [5 empty] | Total Writing time in Hours | BTC 1 Execution Time in Hours | BTC 2 Execution Time in Hours | BTC 3 - Full Sys Test Time in Hours
BTC1 and BTC2 Totals |  |  | 624 | 1313 | 1937 | 10.4 | 17.2167 | 4.6667 | 27.2833
Build 1 |  |  | 604 | 1033 | 1637
Verify the username field is visible- Homepage | 1 | 1 | 2 | 3 | 5
Verify texts can be entered in the username field - Homepage | 1 | 1 | 2 | 3 | 5
Verify an appropriate user/error message appears when leaving the username field blank - Homepage | 1 | 1 | 3 | 5 | 8
Verify an appropriate user/error message appears when entering only spaces in the username field -Home Page | 1 | 1 | 3 | 5 | 8
Verify Username cannot be above 30 characters - Homepage | 1 | 1 | 4 | 5 | 9
Verify Username accepts 1-30 characters - Homepage | 1 | 1 | 4 | 8 | 12
Verify Username cannot accept numerical characters - Homepage | 1 | 1 | 4 | 8 | 12
Verify the password field visible- Homepage |  | 1 | 2 | 3 | 5
Verify texts can be entered in the password field - Homepage | 1 | 1 | 3 | 5 | 8
Verify an appropriate user/error message appears when leaving the password field blank - Homepage | 1 | 1 | 4 | 6 | 10
Verify Password cannot be above 30 characters - Homepage | 1 | 1 | 5 | 8 | 13
Verify Password accepts 1-30 characters - Homepage | 1 | 1 | 5 | 8 | 13
Verify the username and password can't be logged if they haven't been preregistered - Homepage | 1 | 1 | 5 | 8 | 13
Verify forgot password option is visible - Homepage | 1 | 1 | 2 | 4 | 6
Verify that clicking the forgot password 'option' navigates to the "Forgot Password Page" - Homepage | 1 | 1 | 4 | 6 | 10
Verify register 'option' is visible- Homepage | 1 | 1 | 2 | 4 | 6
Verify the register 'option' is clickable - Homepage | 1 | 1 | 2 | 5 | 7
Verify that clicking the register 'option' navigates to the "New User Registration Page". - Homepage | 1 | 1 | 3 | 6 | 9
Verify successful log in navigates to the "Search Hotel Page" - Homepage | 1 | 1 | 4 | 8 | 12
Verify the email field is visible- Forgot Password Page | 1 | 1 | 2 | 5 | 7
Verify texts can be entered in the email field - Forgot Password Page | 1 | 1 | 3 | 4 | 7
Verify an appropriate user/error message appears when leaving the email field blank - Forgot Password Page | 1 | 1 | 5 | 10 | 15
Verify Email cannot be above 50 alphanumeric characters - Forgot Password Page | 1 | 1 | 5 | 8 | 13
Verify Email accepts 1-50 alphanumeric characters - Forgot Password Page | 1 | 1 | 5 | 7 | 12
Verify Email cannot accept invalid email format - Forgot Password Page | 1 | 1 | 5 | 10 | 15
Verify the username field is visible-New User Registration Page | 1 | 1 | 2 | 3 | 5
Verify texts can be entered in the username field - New User Registration Page | 1 | 1 | 2 | 4 | 6
Verify an appropriate user/error message appears when leaving the username field blank - New User Registration Page | 1 | 1 | 4 | 8 | 12
Verify the password field is visible - New User Registration Page | 1 | 1 | 2 | 3 | 5
Verify texts can be entered in the password field - New User Registration Page | 1 | 1 | 2 | 5 | 7
Verify an appropriate user/error message appears when leaving the password field blank - New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify an appropriate user/error message appears when entering only spaces in the password field -New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify Password accepts 8-30 alphanumeric characters- New User Registration Page | 1 | 1 | 3 | 6 | 9
Verify Password cannot be above 30 alphanumeric characters - New User Registration Page | 1 | 1 | 2 | 5 | 7
Verify Password cannot be below 8 alphanumeric characters - New User Registration Page | 1 | 1 | 2 | 5 | 7
Verify the full name field is visible- New User Registration Page | 1 | 1 | 2 | 3 | 5
Verify texts can be entered in the full name field - New User Registration Page | 1 | 1 | 2 | 4 | 6
Verify an appropriate user/error message appears when leaving the full name field blank - New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify an appropriate user/error message appears when entering only spaces in the full name field -New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify full name accepts 1-50 alpha characters including spaces- New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify full name can't accept numerical - New User Registration Page | 1 | 1 | 5 | 10 | 15
Verify full name cannot be above 50 alpha characters including spaces - New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify full name cannot accept only spaces without entering alpha characters - New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify full name cannot accept special characters - New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify the email address field is visible- New User Registration Page | 1 | 1 | 3 | 5 | 8
Verify texts can be entered in the email address field - New User Registration Page | 1 | 1 | 3 | 5 | 8
Verify an appropriate user/error message appears when leaving the email address field blank - New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify an appropriate user/error message appears when entering only spaces in the email address field -New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify the email address field accepts 1-50 alphanumeric and special characters - New User Registration Page | 1 | 1 | 4 | 8 | 12
Verify the email address field cannot accept above 50 alphanumeric and special characters - New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify there is a Captcha Text field - New User Registration Page | 1 | 1 | 3 | 5 | 8
Verify texts can be entered in the Captcha text field - New User Registration Page | 1 | 1 | 3 | 5 | 8
Verify the Captcha Text field label reads "Captcha Text" - New User Registration Page | 1 | 1 | 2 | 5 | 7
Verify an appropriate user/error message appears when leaving the Captcha Text field blank - New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify an appropriate user/error message appears when entering only spaces in the Captcha Text field -New User Registration Page | 1 | 1 | 4 | 10 | 14
Verify that the Captcha text field accepts 1-30 alpha characters - New User Registration Page | 1 | 1 | 4 | 8 | 12
Verify that the Captcha text field cannot accept above 30 alpha characters - New User Registration Page | 1 | 1 | 3 | 5 | 8
Verify that the Captcha text field cannot accept numerical characters - New User Registration Page | 1 | 1 | 5 | 10 | 15
Verify that the Captcha text field cannot accept special characters - New User Registration Page | 1 | 1 | 5 | 10 | 15
Verify an appropriate user/error message appears when the Captcha Text field doesn't match Captcha Image - New User Registration Page | 1 | 1 | 5 | 12 | 17
Verify the First Name field is visible -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify texts can be entered in the First Name field -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify an appropriate user/error message appears when leaving the First Name field blank -Book a Hotel Page | 1 | 1 | 10 | 18 | 28
Verify First Name accepts 1-30 alpha characters including spaces -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify First Name cannot be above 30 alpha characters including spaces -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify First Name field can't accept numerical characters -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify First Name cannot accept only spaces without entering alpha characters -Book a Hotel Page | 1 | 1 | 10 | 18 | 28
Verify First Name cannot accept numerical and special characters -Book a Hotel Page | 1 | 1 | 12 | 19 | 31
Verify the Last Name field is visible -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify texts can be entered in the Last Name field -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify an appropriate user/error message appears when leaving the Last Name field blank -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify Last Name accepts 1-30 alpha characters including spaces -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify Last Name cannot be above 30 alpha characters including spaces -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify Last Name field can't accept alpha and special characters -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify Last Name cannot accept only spaces without entering alpha characters -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify Last Name cannot accept numerical and special characters -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify the Billing Address field is visible -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify texts can be entered in the Billing Address field -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify an appropriate user/error message appears when leaving the Billing Address field blank -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify an appropriate user/error message appears when entering only spaces in the Billing Address field -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify Billing Address accepts 1-300 alphanumeric characters including spaces -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify Billing Address cannot be above 300 alphanumeric characters including spaces -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify the Billing Address field label reads “Billing Address” -Book a Hotel Page | 1 | 2 | 10 | 16 | 26
Verify Billing Address cannot accept special characters - Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify the Credit Card Number field is visible -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify texts can be entered in the Credit Card Number field -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify an appropriate user/error message appears when leaving the Credit Card Number field blank -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify an appropriate user/error message appears when entering only spaces in the Credit Card Number field -Book a Hotel Page |  | 1 | 12 | 18 | 30
Verify Credit Card Number accepts 1-16 numerical characters -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify Credit Card Number cannot be above 16 numerical characters -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify Credit Card Number cannot accept alpha characters - Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify the Credit Card Type field is visible - Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify the CVV field is visible -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify texts can be entered in the CVV field -Book a Hotel Page | 1 | 1 | 10 | 16 | 26
Verify an appropriate user/error message appears when leaving the CVV field blank -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify an appropriate user/error message appears when entering only spaces in the CVV field -Book a Hotel Page | 1 | 1 | 12 | 18 | 30
Verify CVV accepts 3-4 numerical characters -Book a Hotel Page |  | 1 | 12 | 18 | 30
Verify CVV field can't accept alpha and special characters -Book a Hotel Page |  | 1 | 12 | 18 | 30
Verify CVV cannot be above 4 numerical characters -Book a Hotel Page |  | 1 | 12 | 18 | 30
Verify CVV cannot be below 3 numerical characters -Book a Hotel Page |  |  | 12 | 18 | 30
Build 2 |  |  | 20 | 280 | 300
Assume 20 impacted test cases had defect fixes to retest | 2 | 1 | 20 | 280 | 300
Build 3 - Full System Test |  |  | 0 | 1637 | 1637
Retesting all previous test cases | 2 | 1 | 0 | 1637 | 1637
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How important is this test case: 1) very important and needs to be executed, 2) moderately important and should be executed, 3) trivial and could be removed if you ran out of time, typically things like spelling and placement of objects on the screen
Note on F107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the total execution time for BTC2/Build 2, just divide by 60 to convert to hours before putting into the Schedule & Costs tab
Note on F109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the total execution time for BTC2/Build 2, just divide by 60 to convert to hours before putting into the Schedule & Costs tab

## Schedule & Costs
WBS | Task Name | Duration | % | QA Lead | % | QA Tester 1 | % | QA Tester 2 | % | Developer 1 | % | Developer 2 | % | Business Analyst | % | Project Manager | % | QA Manager | Total
607 | Name of Project | 374.6167 | [16 empty] | 60020.1333
607.1 | Planning | 60 |  | 38 |  | 4 |  | 4 |  | 4 |  | 4 |  | 2 |  | 4 |  | 2 | 3224
607.1.1 | Initial Analysis and Costing | 8 | 100% | 6 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0 | 100% | 1 | 100% | 1 | 416
607.1.2 | Develop Initial Schedule | 10 | 100% | 8 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0 | 100% | 2 | 0% | 0 | 520
607.1.3 | Develop Test Plan | 6 | 100% | 8 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 50% | 0 | 0% | 0 | 0% | 0 | 416
607.1.4 | Test Plan Inspection Meeting | 8 | 100% | 2 | 0% | 0 | 0% | 0 | 100% | 2 | 100% | 2 | 100% | 2 | 0% | 0 | 0% | 0 | 416
607.1.5 | Update/Rework Test Plan | 8 | 100% | 8 | 0% | 0 | 0% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 0% | 0 | 0% | 0 | 416
607.1.6 | Requirement Inspection | 8 | 100% | 2 | 0% | 0 | 0% | 0 | 100% | 2 | 100% | 2 | 100% | 0 | 100% | 1 | 100% | 1 | 416
607.1.7 | Setup QA Lab | 12 | 100% | 4 | 100% | 4 | 50% | 4 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 624
607.2 | Development | 70.4 |  | 39.4667 |  | 31.4667 |  | 19.4667 |  | 4 |  | 4 |  | 4 |  | 2 |  | 2 | 5532.8
607.2.1 | Prepare Test Cases | 10.4 | 100% | 3.4667 | 0.33333 | 3.4667 | 0.11111 | 3.4667 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 540.8
607.2.2 | Prepare a Tracebility Matrix | 4 | 100% | 4 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 208
607.2.3 | Review Test Cases/Scenarios | 12 | 100% | 12 | 100% | 12 | 50% | 4 | 100% | 0 | 100% | 0 | 100% | 0 | 0% | 0 | 0% | 0 | 1456
607.2.4 | Test Case/Scenario Inspection Meeting | 12 | 100% | 2 | 100% | 2 | 50% | 6 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 100% | 0 | 832
607.2.5 | Update/Rework Test Cases/Scenarios | 12 | 100% | 12 | 100% | 12 | 50% | 4 | 100% | 0 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 1456
607.2.6 | Estimate Update | 4 | 100% | 4 | 100% | 0 | 50% | 0 | 100% | 0 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 208
607.2.7 | Test Readiness Meeting | 16 | 100% | 2 | 100% | 2 | 50% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 832
607.3 | Testing Build 1 | 67.2167 |  | 29.7389 |  | 25.7389 |  | 17.7389 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | 4327.2667
607.3.1 | Environment Setup | 6 | 100% | 2 | 100% | 2 | 50% | 2 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 312
607.3.2 | Test Case Maintenance | 6 | 100% | 2 | 0% | 2 | 0% | 2 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 312
607.3.3 | Prepare Test Set | 4 | 100% | 4 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 208
607.3.4 | Smoke Test | 6 | 100% | 2 | 100% | 2 | 50% | 2 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 312
607.3.5 | JIRA TIR Testing | 12 | 100% | 12 | 100% | 12 | 50% | 4 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 1456
607.3.6 | Test Execution - BTC 1 | 17.2167 | 100% | 5.7389 | 0.33333 | 5.7389 | 0.11111 | 5.7389 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 895.2667
607.3.7 | BTC 2 Test Readiness Meeting | 16 | 100% | 2 | 100% | 2 | 50% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 832
607.4 | Testing Build 2 | 49 |  | 32.5 |  | 24.5 |  | 15 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | 4264
607.4.1 | Environment Setup | 10 | 100% | 10 | 100% | 10 | 50% | 5 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 1300
607.4.2 | Test Case Maintenance | 1 | 100% | 1 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 52
607.4.3 | Prepare Test Set | 7 | 100% | 7 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 364
607.4.4 | Smoke Test | 10 | 100% | 10 | 100% | 10 | 50% | 5 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 1300
607.4.5 | JIRA TIR Testing | 5 | 100% | 2.5 | 100% | 2.5 | 50% | 3 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 416
607.4.7 | SYSTEM Test Readiness Meeting | 16 | 100% | 2 | 100% | 2 | 50% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 832
607.5 | Full System Test | 171.2833 |  | 304.0944 |  | 275.0944 |  | 147.0944 |  | 18 |  | 18 |  | 18 |  | 18 |  | 425.6167 | 63642.8
607.5.1 | Test Execution - Full System Test | 27.2833 | 100% | 9.0944 | 100% | 9.0944 | 50% | 9.0944 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 1418.7333
607.5.2 | Customer Acceptance Test Readiness Meeting | 16 | 100% | 2 | 100% | 2 | 50% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 832
607.6 | Customer Test | 128 |  | 128 |  | 128 |  | 64 |  | 8 |  | 8 |  | 8 |  | 8 |  | 8 | 18720
607.6.1 | CAT Testing | 120 | 100% | 120 | 100% | 120 | 50% | 60 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 22213
607.6.2 | Root Cause Analysis and DRE | 8 | 100% | 8 | 100% | 8 | 50% | 4 | 100% | 8 | 100% | 8 | 100% | 8 | 100% | 8 | 100% | 8 | 3120
607.7 | Recurring Tasks | 460.6167 |  | 37 |  | 8 |  | 8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 407.6167 | 23952.0667
607.7.1 | QA Management | 374.6167 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 374.6167 | 19480.0667
607.7.2 | Project Meetings | 32 | 100% | 8 | 100% | 8 | 50% | 8 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 8 | 1664
607.7.3 | Status Reporting | 28 | 100% | 14 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 14 | 1456
607.7.4 | Schedule Maintenance | 8 | 100% | 4 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0 | 0% | 4 | 416
607.7.5 | Risk/Change Management | 14 | 100% | 7 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 100% | 0 | 100% | 0 | 0% | 7 | 728
607.7.6 | Test Plan Maintenance | 4 | 100% | 4 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 208
High Level Schedule Overview
| Total (days) | 47
| Total (weeks) | 9.4
| Total (Months) | 2.1692
*Note: All the totals are rounded up
Schedule by Phase
| Planning | 1.5 | weeks | 7.5 | days
| Development | 1.76 | weeks | 8.8 | days
| Testing Build 1/BTC 1 | 1.6804 | weeks | 8.4021 | days
| Testing Build 2/BTC 2 | 1.225 | weeks | 6.125 | days
| Customer Acceptance Test (CAT) | 3.2 | weeks | 16 | days

## Rates and Travel Costs
ID | Item | Units | Total
1 | Personnel
1.1 | Resource Rate | $CAN/hrs | 52
1.2 | Labor | hrs/week | 40
2 | Travel
2.1 | Flight | $CAN | 2650
2.2 | Hotel | $CAN | 2115
2.3 | Vehicle | $CAN | 723
2.4 | Per diem | $CAN | 75 | per person/per day
2.5 | Employees traveling | # | 3

## Requirements (hidden)
ID | Item | Qty
1. Hardware Requirements
1.1 | Laptop | 3
1.2 | Server | 1
1.3 | Laptop accessories (mouse, video export cables, network cable) | 3
1.5 | Facilities (War room) | 1
1.6 | Access Sharing Platform (Teams, Sharepoint & Skype for Biz) | 3
1.7 | Incident Manager Access (JIRA) | 3
*Add one of your own
2. Software Requirements
2.1 | Windows 10 Professional Edition | 3
2.4 | Web browser (Mozilla Firefox & Google Chrome) | 3
2.7 | Incident Manager (JIRA) | 1
*Add one of your own
3. Assumptions
3.1 | 3 qualified QA testers will be avaialbe when required
3.2 | All hardware and software will be delivered during the development phase
3.3 | The scope of the project will not increase, no new requirements will be introduced
3.4 |  |  | *Add at least 3 more of your own
3.5
3.6
3.7
3.8
3.9
3.1